## Sheet1
Planned Time
Month |  | November |  |  |  | December | [7 empty] | January |  |  |  | TOTAL
Week |  | 18-24 |  | 25-01 |  | 2-8 |  | 9-15 |  | 16-22 |  | 23 - 29 |  | 30 - 5 |  | 06 - 10 |  | Initial Forecast | Updated Forecast | Estimated costs | Revenue
|  | Forecast | Updated Forecast | Forecast | Updated Forecast | Forecast | Updated Forecast | Forecast | Updated Forecast | Forecast | Updated Forecast | Forecast | Updated Forecast | Forecast | Updated Forecast | Forecast | Updated Forecast
Resource
Carmen |  | 8 | 8 | 10 | 10 | 6 | 6 | 8 | 8 | 10 | 10 | 4 | 4 | 10 | 10 | 10 | 10 | 66 | 66 | 3102
Abri |  | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 54 | 54 | 1944
Petrana |  | 6 | 6 | 8 | 8 | 15 | 15 | 20 | 20 | 20 | 20 | 10 | 10 | 15 | 15 | 20 | 20 | 114 | 114 | 4560
Niki |  | 3 | 3 | 6 | 6 | 15 | 15 | 20 | 20 | 20 | 20 | 5 | 5 | 15 | 15 | 20 | 20 | 104 | 104 | 4160
Beata |  | 5 | 5 | 6 | 6 | 15 | 15 | 20 | 20 | 20 | 20 | 10 | 10 | 20 | 20 | 20 | 20 | 116 | 116 | 4640
Jan |  | 3 | 3 | 6 | 6 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 16 | 16 | 89 | 89 | 3916
Marianna |  | 1 | 1 | 1 | 1 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 21 | 21 | 1680
[18 empty] | 564 | 564 | 24002 | 47320
Initial Forecast |  | 30 |  | 47 |  | 81 |  | 97 |  | 94 |  | 45 |  | 76 |  | 94 |  |  |  |  | 23318
Updated Forecast |  |  | 30 |  | 47 |  | 81 |  | 97 |  | 94 |  | 45 |  | 76 |  | 94
* Initial Forecast done at 25.11
* Updated Forecast is adjusted every week, past time is updated to actuals and future time adjusted based on discovery process
Hourly charge
Niki | 40
Abri | 36
Carmen | 47
Jan | 44
Petrana | 40
Beata | 40