# STATEMENT OF WORK (SOW)

## Rental App Development

This SOW (“Agreement”) made and effective as of January 6th, 2025 (the “Effective Date”) by and between Swan Softweb Solutions, LLC (“Developer ”),, and Markman Group LLC (“Client”), sets forth the agreement whereby Developer agrees to provide services to Markman Group LLC pursuant to the terms and conditions herein.

### 1. INTRODUCTION

This Statement of Work ("SOW") outlines the terms and conditions under which the Developer will provide software development services to the Client for the development of a Rental Application as described herein.

### 2. PROJECT OVERVIEW

The Developer will design, develop, and deliver a fully functional Rental Application according to the specifications detailed in the feature document and prototype previously agreed upon. The application will facilitate full rental lifecycle, covering everything from order creation to return processing at the warehouse, enabling tracking of all essential checkpoints, stock management, and real-time reporting for operational control. Rental Application consists on three modules:

- Rental Process Management: Covers the entire rental process from order creation to return processing. It allows manual adjustments when needed, ensuring flexibility and accuracy in handling rentals

- Warehouse Management: Tracks and manages the availability and usage of inventory in real-time. This module ensures accurate stock levels, preventing discrepancies, and supports manual adjustments when required.

- Reporting Module: The Reporting module provides high-level reports to track key rental operations and performance. These reports include essential data such as Revenue, Stock, Stock Movement, In Transit, Planned Removal, Planned Deliveries and Equipment Utilization)

### 3. TIMELINE AND DELIVERABLES

#### 3.1 Project Timeline

The project duration will be 16 weeks, commencing on January 6, 2025, with a final delivery date during the week of April 21st, 2025

#### 3.2 Milestones and Deliverables

The project will be divided into the following milestones/sprints:

| Milestone/ Sprint | Description | Estimated Completion |  |
| --- | --- | --- | --- |
| 1 | Authorisation, User Permission, User List(Authorization, Workflow and Master Data (Products/Warehouse) | Week 2 (2025.01.20) |  |
| 2 | Master Data (Account Managers, Customers), Stock Adjustment, Rent Process | Week 4 (2025.02.03) |  |
| 3 | Rent Process (Order and Recurring Order) | Week 6 (2025.02.17) |  |
| 4 | Rent Process (Return Order, Order Detail Stages: Create Delivery, Pickup Ticket and Check out) | Week 8 (2025.03.03) |  |
| 5 | Rent Process (Order Detail Stages: Delivered to Customer, Create Return Deliveries, Pickup Ticket for Return Delivery, Check In, Inspection Completed) | Week 10 (2025.03.15) |  |
| 6 | Global Search and Home – Map (Search, Zoom Controls, Full-Screen Mode, Street View integration, Location Pins& Home, Responsiveness and Error Handling) | Week 12 (2025.03.31) |  |
| 7 | Reports (Revenue Report, Stock Report, Stock Movement, In Transit) | Week 14 (2025.04.10) |  |
| 8 | Reports (Planned Removal, Planned Deliveries, Equipment Utilization Report) and Inbox (Request, Accept and Decline) | Week 16 (2025.04.21) |  |

#### Upon final project completion, in addition to the delivery of all milestones, all related code documentation shall be provided.

#### 3.3 Acceptance Criteria

Each milestone will be considered complete when the Developer delivers the associated functionality according to the specifications in the feature document and prototype, and the Client approves the delivery through testing.

### 4. PAYMENT TERMS

#### 4.1 Total Contract Value

The total payment for the development services will be $15,720

#### 4.2 Payment Schedule

### The project's payment structure consists of two payments: 50% upon reaching the midpoint of all milestones, and the remaining 50% upon final project delivery.

### 5. QUALITY ASSURANCE

#### 5.1 Quality Requirements

All features described in the feature document and prototype must be included in the final deliverable. The Developer will conduct thorough testing before delivering each milestone to ensure compliance with the specifications.

#### 5.2 Discrepancy Resolution

Any discrepancies between the delivered product and the specifications in the feature document and prototype must be resolved within 5 working days of identification by the Client.

#### 5.3 Testing Period

The Client will have a two-months testing period following the final delivery to ensure all requirements specified in the feature document are met. The final payment is contingent upon successful completion of this testing period.

### 6. CHANGE MANAGEMENT

#### 6.1 Change Request Process

Any changes to the project scope, timeline, or deliverables must be documented in a written Change Request and approved by both parties.

#### 6.2 Impact Assessment

All Change Requests will include an assessment of the impact on the project timeline, deliverables, and cost.

### 7. COMMUNICATION

#### 7.1 Regular Updates

The Developer will provide weekly progress updates to the Client, including:

- Completed tasks

- In-progress tasks

- Upcoming tasks

- Any issues or risks identified

#### 7.2 Point of Contact

Each party will designate a primary point of contact for all project-related communications.

### 8. INTELLECTUAL PROPERTY

All intellectual property rights to the developed software will transfer to the Client, including source code, documentation, and any other materials created for this project.

### 9. CONFIDENTIALITY AND NON-DISCLOSURE

#### 9.1 Definition of Confidential Information

"Confidential Information" means all non-public information disclosed by either party ("Disclosing Party") to the other party ("Receiving Party"), whether orally, in writing, or by any other means, that is designated as confidential or that reasonably should be understood to be confidential given the nature of the information and the circumstances of disclosure. Confidential Information includes, but is not limited to:

- Business plans, strategies, forecasts, and analyses

- Financial information and projections

- Customer and supplier information

- Technical specifications, designs, drawings, and blueprints

- Software code, algorithms, and development methodologies

- Product plans, prototypes, and development roadmaps

- Marketing strategies and campaigns

- Employee and contractor information

- Trade secrets and proprietary technologies

- The terms and conditions of this SOW

#### 9.2 Obligations of Receiving Party

The Receiving Party agrees to:

a) Use the Confidential Information solely for the purpose of performing its obligations under this SOW;

b) Protect the Confidential Information with the same degree of care it uses to protect its own confidential information, but in no event less than reasonable care;

c) Limit access to Confidential Information to its employees, contractors, and agents who have a need to know such information for the purpose of performing obligations under this SOW and who are bound by confidentiality obligations at least as restrictive as those contained herein;

d) Not disclose the Confidential Information to any third party without prior written consent from the Disclosing Party;

e) Promptly notify the Disclosing Party of any unauthorized use or disclosure of Confidential Information and cooperate with the Disclosing Party to help regain possession of such Confidential Information and prevent its further unauthorized use or disclosure.

#### 9.3 Exclusions

The obligations set forth in Section 9.2 do not apply to information that:

a) Was known to the Receiving Party prior to receipt from the Disclosing Party without an obligation of confidentiality;

b) Is or becomes publicly available through no fault of the Receiving Party;

c) Is rightfully received by the Receiving Party from a third party without a duty of confidentiality;

d) Is independently developed by the Receiving Party without use of or reference to the Disclosing Party's Confidential Information;

e) Is required to be disclosed by law or court order, provided that the Receiving Party gives the Disclosing Party prompt written notice of such requirement prior to disclosure and assists in obtaining an order protecting the information from public disclosure.

#### 9.4 Duration of Confidentiality Obligations

The confidentiality obligations set forth in this section shall remain in effect during the term of this SOW and for a indefinite period thereafter. Any trade secrets shall be protected for as long as they qualify as trade secrets under applicable law.

#### 9.5 Return of Materials

Upon termination of this SOW or upon the Disclosing Party's request, the Receiving Party shall promptly return or destroy all materials containing Confidential Information, including all copies, notes, or other documents containing such Confidential Information, and provide written certification of such return or destruction if requested by the Disclosing Party.

### 10. TERMINATION

Either party may terminate this agreement with written notice if the other party materially breaches the terms of this SOW and fails to remedy such breach within 15 days of receiving written notice.

### 11. SIGNATURES

This Statement of Work is agreed to and accepted by:

Client:

Name: _______________________

Signature: ___________________

Date: _______________________

Developer:

Name: _______________________

Signature: ___________________

Date: _______________________