## PRIORITY LIST
ID | Sheet & ID | Description | Status | Target Date | Notes
1 | Rent Process - Checkout - 3 | Typo | IMPLEMENTED | 2024-08-08
2 | Rent Process - Checkout - 1 | Checkout date | IMPLEMENTED | 2024-08-08
3 | Rent Process - Pickup Ticket - 1 | Pick-up date | IMPLEMENTED | 2024-08-08
4 | Rent Process - Pick up Ticket - 1 (second sheet for returns) | Pick-up date | IMPLEMENTED | 2024-08-08
5 | Rent Process - Inspection completed - 2 | Inspection date | IMPLEMENTED | 2024-08-08
6 | Master Data - Customers - 1 | Left Navigation Panel | IMPLEMENTED | 2024-08-08
7 | Rent Process - Orders - 7 | Delivery Order break down | IMPLEMENTED | 2024-08-08
8 | Rest of the tabs - Inbox | Visuo + Accept/Decline button (redirection) | IMPLEMENTED | 2024-08-08 | for prorotype is enough to have one notification linked
9 | Rent Process - Orders - 6 | Rental Period | LET'S REVIEW | 2024-08-08
10 | Rest of the tabs - Reports | Visuo | NOT STARTED | 2024-08-09
11 | Rent Process - Create Delivery & Create Return Delivery | Enter PO | NOT STARTED | 2024-08-09 | PO should be red only in case of external currier (only if not filed in)
12 | Rent Process - Delivery to Customer - 1 | Delivery Date | NOT STARTED | 2024-08-09 | should be editable (preloaded as it is now but editable)
13 | Rent Process - Delivery to Customer - 2 | Contract Date | NOT STARTED | 2024-08-09 | cannot be editable
14 | Rent Process - Inspection completed - 4 | Stock Adjustment | NOT STARTED | 2024-08-09 | Validation after stock adjustment - if we do stock adjustment - it still give us error as it does not reconcile. After saving the change and adjusting the stocks, it should be validated and let us continue. E.g. - we should have quantity 14, but during inspection we noticed something and want to enter only 10 - we do stock adjustment of 4 and save - then we should be able to complete inspection with quantity 10 without validation error
15 | Rent Process - Reccuring Orders - 1 | Orginal Order No. | NOT STARTED | 2024-08-09 | Please add to the report colum with original invoice number with hyperlink to it - to have refference to the orginal order. E.g. I create order A123, but recurring period is every 2 months. Therefore in reccuring order I will see reccurring orders B120 & B121 with column holding original order number A123
16
17
18
19
20
21
22
23
Date prec
Location mensie - alebo to full screen ako proposal
Account Manager - si vypytali

## Master Data ---> (hidden)
Master Data Validation | Status
Products | pending validation
Warehouse | validated | full list imported
Customers | validated | 2% of data imported

## Products (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Filter Dates | All filter attributes | 2024-08-07 | to which attribute in the backend these fields are being linked to? Does filters working? I have changed many times, nothing has changed

## Warehouse (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1
2 | [5 empty] | MASTER DATA VALIDATION
[6 empty] | MD Location | MD Address | APP Location | APP Address | Location CHECK | Address CHECK
[6 empty] | Bakersfield | 3876 Allen Rd, Bakersfield, CA 93314 | Bakersfield | 3876 Allen Rd, Bakersfield, CA 93314 | TRUE | TRUE
[6 empty] | Brawley | 803 CA-78, Brawley, CA 92227 | Brawley | 803 CA-78, Brawley, CA 92227 | TRUE | TRUE
[6 empty] | Colusa | 2959 Davison Ct, Colusa, CA 95932 | Colusa | 2959 Davison Ct, Colusa, CA 95932 | TRUE | TRUE
[6 empty] | Corning | 2920 Hwy 99 W, Corning, CA 96021 | Corning | 2920 Hwy 99 W, Corning, CA 96021 | TRUE | TRUE
[6 empty] | Delano | 325 Rd 192, Delano, CA 93215 | Delano | 325 Rd 192, Delano, CA 93215 | TRUE | TRUE
[6 empty] | Hanford | 10757 Energy St, Hanford, CA 93230 | Hanford | 10757 Energy St, Hanford, CA 93230 | TRUE | TRUE
[6 empty] | Hollister | 2241 OLD AIRLINE HWY, PAICINES, CA 95043 | Hollister | 2241 OLD AIRLINE HWY, PAICINES, CA 95043 | TRUE | TRUE
[6 empty] | Lodi | 1301 Armstrong Rd, Lodi, CA 95242 | Lodi | 1301 Armstrong Rd, Lodi, CA 95242 | TRUE | TRUE
[6 empty] | Old River | 9213 Old River Rd. Bakersfield, CA 93311 | Old River | 9213 Old River Rd. Bakersfield, CA 93311 | TRUE | TRUE
[6 empty] | Yuma | 8853 S Avenue 7 E, Yuma, AZ 85365 | Yuma | 8853 S Avenue 7 E, Yuma, AZ 85365 | TRUE | TRUE

## Customers (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Left Navigation Panel | Navigation Panel | 2024-08-07 | Side navigation panel should be same across all windows in rental app - why do we see navigation panel from proposal app? | IMPLEMENTED
2 | Validation Points | Import Customer | 2024-08-07 | I see blanks or '-' values in some rows - do we have any validation in the back-end to do not allow import customers without full data? | QUEUE
[6 empty] | Fields | Required? | Comment
[6 empty] | Internal ID | Yes
[6 empty] | ID | Yes
[6 empty] | Name | No | empty value found
[6 empty] | Sales Rep | No | empty value found
[6 empty] | Billing Address 1 | No | empty value found
[6 empty] | Billing Address 2 | No | empty value found
[6 empty] | Billing City | No | empty value found
[6 empty] | Billing State/Province | No | empty value found
[6 empty] | Billing Zip | No | empty value found
[6 empty] | Billing Country | No | empty value found

## Orders (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Free Text Columns | Link Netsuite, Account Manager, Region, Customer Emai | 2024-08-07 | information we are having in the Master Data about the customer should be prefilled when customer selected | REQUESTED BY CLIENT
2 | Location Columns | Delivery Location & Pick-up location | 2024-08-07 | should be loaded from the Master Data
3 | Adding line items | Item drop-down | 2024-08-07 | unable to select another item from the drop-down in case I want to add second item to the basket | PROTOTYPE VERSION
4 | Price | Price | 2024-08-07 | shouldn't be price prefiled from product master data? | NN REVIEW
5 | Rent Amount calculation | Rent Amount | 2024-08-07 | rent amount should be calculated from the order lines | NN REVIEW
6 | Rental period | Rental period | 2024-08-07 | will be reviewed once released | LET'S DISCUSS
7 | Delivery Order break down | Delivery Order | 2024-08-07 | as per Marianna's comment via Teams (we should have detailed view of the orders to see what stage they are at) | IMPLEMENTED
8 | Diagram | Process flow | 2024-08-07 | how process flow will be displayed in case of multiple delivery orders?
Water Source & Crop requested by client as free text

## Return Orders (hidden)
Let's discuss on the call (edit button is not working properly) | STATUS

## Reccuring Orders (hidden)
Let's discuss on the call (edit button is not working properly)
how we will refference the reccuring order back to original order?

## Create Delivery (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Tick option | Ticket button | 2024-08-07 | either yellow highlighted should not be an option or should be working properly - when ticked, all items will be ticked - when unticked, all items will be unticked - in case user wants to customize and will manually untick one or more items it will be automatically unticked
2 | Save | Save | 2024-08-07 | unable to save/create delivery - what is the reason?
3 | Enter PO number red | Enter PO | 2024-08-08 | PO should be red only in case of external currier
4 | Customer Location | Customer Location | 2024-08-08 | Customer Location should be actual location not pick from order as noone will remember what was on the order before
5 | Contract Start Date | Contract Start Date | 2024-08-08 | Create delivery I think we should have visible contract start date and delivery date will be prefilled by person manually
6
7
8

## Pickup Ticket (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Pickup date | Pickup date | 2024-08-07 | pickup date default value should be today's date also, for second delivery ID - if date is empty and status is filled in - it will let me continue - therefore we will have incorrect data as we will be missing pick-up date we should not be able to select future dates - only past dates
2 | Unable to adjust | Status |  | how we are going to do corrections? - let's discuss
3
4
5
6
7
8

## Check out (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Checkout date | Checkout date | 2024-08-07 | pickup date default value should be today's date | IMPLEMENTED
2 | Unable to adjust | Status |  | how we are going to do corrections? - let's discuss
3 | Typo | Warning message | 2024-08-07 | Quantity does not match. Please Resolve!! | IMPLEMENTED
4 | Warning | Warning message | 2024-08-07 | Warning only for first line item
5
6
7
8

## Delivery to Customer (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Dates | Delivery Date | 2024-08-08 | should be editable (preloaded as it is now but editable)
2 | Contract Date editable | Contract Date | 2024-08-08 | cannot be editable
3
4
5
6
7
8

## Create Return Delivery (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Tick option | Ticket button | 2024-08-07 | either yellow highlighted should not be an option or should be working properly - when ticked, all items will be ticked - when unticked, all items will be unticked - in case user wants to customize and will manually untick one or more items it will be automatically unticked applicable also for Update Return Delivery screen
2 | Save | Save | 2024-08-07 | unable to save/create delivery - what is the reason?
3 | Dates | Delivery Date & Pick up date | 2024-08-07 | we should not be able to choose date in the past
4 | Delivery ID | Delivery ID | 2024-08-07 | do we have to fill in all details for both return deliveries? --- let's discuss
5 | Contract End Date not editable | Contract End Date | 2024-08-08 | Contract End Date should not be editable
6 | Pick Up Site prefilled | Pick Up Site | 2024-08-08 | should be prefiled with data entered in previous stages
7 | Customer Location prefilled | Customer Location | 2024-08-08 | should be prefiled with data entered in previous stages
8 | Enter PO number red | Enter PO | 2024-08-08 | PO should be red only in case of external currier

## Pick up Ticket (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Dates | Delivery Date & Pick up date | 2024-08-07 | should be by default today's date I am able to continue without having second Pickup Date filled in, why?
2 | Only pending DL | Delivery ID | 2024-08-08 | we should see only one DL based on agreed pick-up date not two - picker needs to see only current workload and not future/or past
3 | Pick Up Site prefilled | Pick Up Site | 2024-08-08 | should be prefiled with data entered in previous stages
4 | Customer Location prefilled | Customer Location | 2024-08-08 | should be prefiled with data entered in previous stages
5
6
7
8

## Check in (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Unable adjust stock | Save | 2024-08-07 | unable to 'Save' adjustments - Save button is not working
2 | Dates | Checkin Date | 2024-08-07 | should be today's date without possibility to choose future dates
3 | Quantity | Minus Quantity | 2024-08-08 | prefilled | IMPLEMENTED
4 | Validation after stock adjustment | Stock Adjustment | 2024-08-08 | if we do stock adjustment - it still give us error as it does not reconcile
5
6
7
8

## Inspection completed (hidden)
ID | Name | Attributes | Date | NN: Comment | STATUS
1 | Message X | Warning Message (Quantity) | 2024-08-07 | when I click X in the warning message nothing happens - remove X
2 | Dates | Inspection Date | 2024-08-07 | should be today's date without possibility to choose future dates | IMPLEMENTED
3 | Quantity | Minus Quantity | 2024-08-08 | prefilled | IMPLEMENTED
4 | Validation after stock adjustment | Stock Adjustment | 2024-08-08 | if we do stock adjustment - it still give us error as it does not reconcile
5
6
7
8

## Stock Adjustments (hidden)
ID | Name | Attributes | Date | NN: Comment | Chetan: Comment
1 | Filters | Internal ID, Family, Location & Parent | 2024-08-07 | Filters do not work, also please make sure they are in the same order as in the table - so it should be Internal ID, Family, Location, Parent
2 | Save button | Save | 2024-08-07 | Unable to save adjustments
3 | Validation check on quantity | Revised Quantity | 2024-08-07 | we should not be able to adjust quantity so revised amount will be minut (we need to get error message same as we have in the workflow) - e.g. in the screenshot above we should not be able to have MINUT QUANTITY over 1583
4 | Action Link | Action | 2024-08-07 | Action button is referencing to the same item all the time, what is the logic here?
5
6
7
8

## Reports (hidden)
Looks much better, but we need to add description, please see below visuo (description will be provided later - put placeholder text) - also the what fields it contains atd. - additional screen with the information
DATA FOR DESCRIPTION OF THE REPORTS
Report Name | Description
Revenue Report | Provides a summary of income generated from equipments rentals, including total revenue, segment breakdown.
Stock Report | Shows inventory levels, including available, reserved, and out-of-service equipment, along with value assessments.
Stock Movement Report | Tracks all movements of equipment, including additions, removals, and transfers between locations.
In Transit | Lists equipment currently being transported between locations or to/from customers.
Planned Removal | Details scheduled pickups or returns of equipment, including dates and locations.
Planned Deliveries | Outlines upcoming equipment deliveries, with delivery dates, destinations, and customer details.
Usage of Equipment | Analyzes how often and how long equipment has been rented, providing insights into utilization rates and demand.
Revenue Report
Description

## Authorization (hidden)
I understand we have 'Permission Metrics' on the top, but as end-user I immediately wants to go to 'pencil' to edit and expect to have permission here too. Please add permission column here with possibility to add roles. All columns listed in the table must be editable in this pop-up.

## Workflow (hidden)
Please clarify why we have Authorization and Workflow permissions separately? Cannot we have it all on one screen with authorization and just split on access to step in the process and notification? - let's discuss

## Inbox (hidden)
I realy like Pick Up message (on right) - something like that we should have for all notifications (as design so hyperlink to the document). In those phases where Accept/Decline button is not applicable, please just drop-it from notification. Hyperlink should navigate me to the specific stage of the process of the order (e.g. in this case pick-up screen of order#PROJ016968) Add updated msg - if completed Read/Unread msg options Also, Accepet/Decline buttom should navigate us to the screen of the step and order I should proces - e.g. in this case Pick-up screen of the order#PROJ016968