## User Bugs
Client |  |  |  | Markman Group
ID | Blockers | Screen | Detailed description of the issue | Status | Effort MIN (with validation testing) | Effort MAX (with validation testing) | Type | Comments
21 | No | 4 Task Mapping | Changing the description for an estimate on step 1 does not change the description on step 4. | In Review |  |  | New Feature Rework
22 | No | 4 Task Mapping | Deleting an estimate on step 1 does not remove it on step 4 | In Porgress | 8 | 12 | New Feature Rework
23 | Yes | 2 Upload CAD file | Dropping file into the "drop files here to upload" results in error "Something went wrong :( ". Same error when selecting a file through the explorer | In Porgress | 5 | 8 | Feature Enhancement | the format should not be tmp but txt file
24 | No | 4 Task Mapping | Refreshing (F5) causes task codes to change order | Open | 6 | 8 | Feature Enhancement | Lars to confirm if sorting is OKAY - same order on all screens (anal. + stage 4 the split between labor and notmal tasks to stay)
25 | Yes | 4 Task Mapping | Refreshing (F5) needs to ask for user approval before reloading the page. Any changes made to estimates appear to only be saved when going to step 5, so if the page is refreshed before moving on, all progress is lost. | Open | 7 | 11 | New Feature Addition | F5 (confirmation on save)/or autosave
27 | No | 4 Task Mapping | When entering items, can we make the description field as large as possible from the beginning, and not only once the first item is entered? | In Porgress | 3 | 5 | Feature Enhancement
28 | No | 4 Task Mapping | Entering item 401020 in an estimate shows description "PVC TEE S40 2" SOC x FPT" whereas the product database correctly shows "PVC TEE S40 2" SOC" | In Porgress |  |  | Functionality Bug | check the mapping between item code & description - vs product master
29 | Yes | 4 Task Mapping | Unable to change an item by changing the item code. First step was selecting an item by entering an item code. Second step, I changed the item by using the drop down in the description. Third step, I tried to enter a new item code to change the item once more, and was unable to do so. | Open | 7 | 10 | Feature Enhancement | already added rows allowed to change description/item code - should be availabel for active row
30 | No | 4 Task Mapping | Searching for an item in the description column does not work for partial strings | In Porgress | 7 | 10 | Feature Enhancement | cross check (similar to NetSuite)
36 | Yes | 5 Generate Estimate | The totals from step don't show up properly on this page. | Open | 6 | 9 | Feature Enhancement | not unit price, confirmation pending
37 | Yes | 5 Generate Estimate | How is Freight adjusted? | In Review |  |  | New Feature Addition | should be to Task Mapping (and set-up as regular task code --) - the product list should be expanded to see noninventory items
39 | Yes | 4 Task Mapping | Using the Upload CAD file, and assigning products to an estimate, the Description and Standard Cost don't update. Also, quantities have decimals, which they shouldn't | Open |  |  | Functionality Bug | clarification needed
40 | Yes | 4 Task Mapping | Adding items accepts any input, not just products specified in the product database. This can happen via the Upload Function (see "Single-C" in screenshot) or via manual entry (see "dog" in screenshot) | Open | 8 | 12 | Feature Enhancement | how the not valid codes are being validated with Upload CAD no valid items should not be populated in the estimate - but should be visible under 'non valid parts' - in assign parts
43 | Yes | 4 Task Mapping | How do I remove an estimate? | Open | 6 | 9 | New Feature Addition
47 | Yes | 4 Task Mapping | All Task Codes available in drop-down | In Porgress |  |  | Functionality Bug
49 | Yes | Products | Attempting to modify the glue / additional material calculator, and I can't find where to do that. I imagine it would be in the Products -> Additional Material tab? | Open |  |  | Feature Enhancement
[5 empty] | 63 | 94
[5 empty] | 1.58 | 2.35
|  |  |  | Blockers | 39 | 59
|  |  |  | No Blockers | 24 | 35

## DropDowns (hidden)
Rental Application Screen | Stage | Status | Type
Opportunity | Opportunity List | Open | Functionality Bug | Issues within the agreed scope that impact the application’s functionality and need fixing.
Products | 1 Select Task Code | In Porgress | Feature Enhancement | Requests to improve or extend existing features, adding value without introducing new functionality.
Labour Cost | 2 Upload CAD File | In Review | New Feature Addition | Requests for entirely new features not included in the original scope or prototype.
Customers | 3 Material List | Done | Future Scope Extension (Phase 2) | Significant adjustments or expansions that will be scheduled for a later phase due to resource and time considerations.
Tasks | 4 Task Mapping |  | New Feature Rework | This category encompasses issues found in newly implemented features that require debugging, corrections, or rework to function as expected according to the original requirements.
Vendors | 5 Generate Estimate
Authorization | 6 Proposal Creation
7 Proposal Preview
8 Final Documents