## User Bugs
|  |  |  | In Review |  | 7
|  |  |  | In Progress |  | 7
|  |  |  | Open |  | 14
Client | [5 empty] | Markman Group
ID | Proposal Application | Blockers | Stage | Detailed description of the issue | Phase | Status | Type
21 | Opportunity | Yes | 4 Task Mapping | Changing the description for an estimate on step 1 does not change the description on step 4. | Third Round | In Review | New Feature Rework
22 | Opportunity | Yes | 4 Task Mapping | Deleting an estimate on step 1 does not remove it on step 4 | Third Round | In Review | New Feature Rework
23 | Opportunity | Yes | 2 Upload CAD file | Dropping file into the "drop files here to upload" results in error "Something went wrong :( ". Same error when selecting a file through the explorer | Third Round | In Review | Feature Enhancement
25 | Opportunity | Yes | 4 Task Mapping | Refreshing (F5) needs to ask for user approval before reloading the page. Any changes made to estimates appear to only be saved when going to step 5, so if the page is refreshed before moving on, all progress is lost. | Third Round | In Progress | New Feature Addition
27 | Opportunity | Yes | 4 Task Mapping | When entering items, can we make the description field as large as possible from the beginning, and not only once the first item is entered? | Third Round | In Review | Functionality Bug
28 | Opportunity | Yes | 4 Task Mapping | Entering item 401020 in an estimate shows description "PVC TEE S40 2" SOC x FPT" whereas the product database correctly shows "PVC TEE S40 2" SOC" | Third Round | In Review | Functionality Bug
29 | Opportunity | Yes | 4 Task Mapping | Unable to change an item by changing the item code. First step was selecting an item by entering an item code. Second step, I changed the item by using the drop down in the description. Third step, I tried to enter a new item code to change the item once more, and was unable to do so. | Third Round | In Progress | Feature Enhancement
30 | Opportunity | Yes | 4 Task Mapping | Searching for an item in the description column does not work for partial strings | Third Round | In Progress | Feature Enhancement
31 | Opportunity | Yes | 4 Task Mapping | In an estimate, deleting the last row (the one with the "Plus") will remove the "Plus" to add a row without adding it to the above row. | Third Round | Open | Feature Enhancement
36 | Opportunity | Yes | 5 Generate Estimate | The totals from step don't show up properly on this page. | Third Round | In Progress | Feature Enhancement
37 | Opportunity | Yes | 5 Generate Estimate | How is Freight adjusted? | Third Round | In Review | New Feature Addition
39 | Opportunity | Yes | 4 Task Mapping | Using the Upload CAD file, and assigning products to an estimate, the Description and Standard Cost don't update. Also, quantities have decimals, which they shouldn't | Third Round | Open | Functionality Bug
40 | Opportunity | Yes | 4 Task Mapping | Adding items accepts any input, not just products specified in the product database. This can happen via the Upload Function (see "Single-C" in screenshot) or via manual entry (see "dog" in screenshot) | Third Round | Open | Feature Enhancement
43 | Opportunity | Yes | 4 Task Mapping | How do I remove an estimate? | Third Round | Open | New Feature Addition
47 | Opportunity | Yes | 4 Task Mapping | All Task Codes available in drop-down | Third Round | In Review | Functionality Bug
53 | Opportunity | Yes | 4 Task Mapping | Totals not calculated for materials | Third Round | Open | Functionality Bug
54 | Opportunity | Yes | 5 Generate Estimate | How is tax rate adjusted? | Third Round | Open | Feature Enhancement
56 | Opportunity | Yes | 5 Generate Estimate | Combined GP is not calculated properly | Third Round | In Progress | Functionality Bug
58 | Opportunity | Yes | 5 Generate Estimate | The "S&H" column for estimates should be blank as we don't charge freight on a materials estimate level, but for the whole project | Third Round | Open | Feature Enhancement
59 | Opportunity | Yes | 5 Generate Estimate | Total GP is not calculated properly. Also, what is GP% indirects? | Third Round | Open | Functionality Bug
60 | Opportunity | Yes | 6 Proposal Creation | At this point, the selectable task codes should correspond to the rows from step 5, since we're looking for the totals of each estimate | Third Round | Open | Functionality Bug
61 | Opportunity | Yes | 5 Generate Estimate | Labor only estimates generated during step 5 don't show up on step 6 | Third Round | In Progress | Functionality Bug
63 | Opportunity | Yes | 6 Proposal Creation | Discuss, this screen is too clunky, in that each estimate takes up too much room. At this stage, we only need to see the task code, description, and total sell price per estimate. Also need ability to add description to each group with multiple lines / ability to add lines | Third Round | Open | Feature Enhancement
65 | Opportunity | Yes | 5 Generate Estimate | GP% - avg | Third Round | In Progress | Functionality Bug
67 | Opportunity | Yes | 7 Proposal Preview | In the proposal, we don't want to see individual tasks anymore, only the groups created in step 6 and the total $ sum of the group components. | Third Round | Open | New Feature Addition
70 | Opportunity | Yes | 7 Proposal Preview | What is Exhibit A - Project Detail? | Third Round | Open | Functionality Bug
71 | Opportunity | Yes | 8 Final documents | Printout needs adjustments - Exhibit A - Project detail again? - Should not show boxes around fields - Remove Trashcan Icons - page breaks need to be smart and intuitive (such as invoice on separate page , don't cut off content from header) | Third Round | Open | Feature Enhancement
76 | Opportunity | Yes | 8 Final documents | Netsuite Extract appears to show the internal ID of the task code. at this stage we need the internal ID of the parts. | Third Round | Open | Feature Enhancement

## DropDowns (hidden)
Rental Application Screen | Stage | Status | Type
Opportunity | Opportunity List | Open | Functionality Bug | Issues within the agreed scope that impact the application’s functionality and need fixing.
Products | 1 Select Task Code | In Porgress | Feature Enhancement | Requests to improve or extend existing features, adding value without introducing new functionality.
Labour Cost | 2 Upload CAD File | In Review | New Feature Addition | Requests for entirely new features not included in the original scope or prototype.
Customers | 3 Material List | Done | Future Scope Extension (Phase 2) | Significant adjustments or expansions that will be scheduled for a later phase due to resource and time considerations.
Tasks | 4 Task Mapping |  | New Feature Rework | This category encompasses issues found in newly implemented features that require debugging, corrections, or rework to function as expected according to the original requirements.
Vendors | 5 Generate Estimate
Authorization | 6 Proposal Creation
7 Proposal Preview
8 Final Documents