## Delivery Plan
TASK NAME | STATUS | ASSIGNED TO | TARGET DATE | 13-01 | 14-01 | 15-01 | 16-01 | 17-01 | 20-01 | 21-01 | 22-01 | 23-01 | 24-01 | 27-01 | 28-01 | 29-01 | 30-01 | 31-01
Upload CAD file ¦ TXT file format to be accepted | In Review | Markman | 17-01-2025
Task Mapping ¦ Description sync between stages | In Review | Markman | 17-01-2025
Task Mapping ¦ Delete sync between stages | In Review | Markman | 17-01-2025
Generate Estimate ¦ Freight | In Review | Markman | 17-01-2025
Task Mapping ¦ Description width | In Review | Markman | 21-01-2025
Task Mapping ¦ Product code and description mapping | In Review | Markman | 21-01-2025
Task Mapping ¦ Labor task codes | In Review | Markman | 21-01-2025
Proposal Preview ¦ Removal of 'Exibit A - Project Detail' | In Progress | Markman | 21-01-2025
Proposal Creation ¦ Task codes sync with stage 5 | In Progress | Markman | 21-01-2025
Task Mapping ¦ Allow change description & code at anytime | In Progress | Markman | 21-01-2025
Task Mapping ¦ Search on partial strings | In Progress | Markman | 21-01-2025
Generate Estimate ¦ GP totals calculation | In Progress | Markman | 24-01-2025
Generate Estimates ¦ Labor only task codes | In Progress | Markman | 24-01-2025
Generate Estimate ¦ Totals on task codes | In Progress | Markman | 24-01-2025
Generate Estimate ¦ GP% calculation | In Progress | Markman | 24-01-2025
Generate Estimate ¦ S&H column (remove) | In Progress | Markman | 24-01-2025
Task Mapping ¦ Task code removal | In Progress | Markman | 24-01-2025
Task Mapping ¦ Save changes on refresh pop-up | In Progress | Markman | 28-01-2025
Task Mapping ¦ Totals immediate-save | In Progress | Markman | 28-01-2025
Generate Estimate ¦ Tax rate editable | Not Started | Markman | 28-01-2025
Task Mapping ¦ Plus to be available anytime | Not Started | Markman | 28-01-2025
Task Mapping ¦ Description & amounts validation of CAD files | Not Started | Markman | PENDING CONFIRMATION
Task Mapping ¦ Validation of CAD products with product list | Not Started | Markman
Final Documents ¦ Netsuite extract adjustment | Not Started | Markman | 28-01-2025
Proposal Creation ¦ Redesign (task code, description, total sell price per estimate - group description with multiple lines) | Not Started | Markman | PENDING CONFIRMATION
Proposal Preview ¦ To mirror Proposal Creation | Not Started | Markman
Final Documents ¦ Printout adjustments | Not Started | Markman | PENDING CONFIRMATION

## Primary Focus
|  |  |  | In Review |  | 7
|  |  |  | In Progress |  | 13
|  |  |  | Open |  | 8
Client | [5 empty] | Markman Group
ID | Proposal Application | Blockers | Stage | Detailed description of the issue | Phase | Status | Type
21 | Opportunity | Yes | 4 Task Mapping | Changing the description for an estimate on step 1 does not change the description on step 4. | Third Round | In Review | New Feature Rework
22 | Opportunity | Yes | 4 Task Mapping | Deleting an estimate on step 1 does not remove it on step 4 | Third Round | In Review | New Feature Rework
23 | Opportunity | Yes | 2 Upload CAD file | Dropping file into the "drop files here to upload" results in error "Something went wrong :( ". Same error when selecting a file through the explorer | Third Round | In Review | Feature Enhancement
25 | Opportunity | Yes | 4 Task Mapping | Refreshing (F5) needs to ask for user approval before reloading the page. Any changes made to estimates appear to only be saved when going to step 5, so if the page is refreshed before moving on, all progress is lost. | Third Round | In Progress | New Feature Addition
27 | Opportunity | Yes | 4 Task Mapping | When entering items, can we make the description field as large as possible from the beginning, and not only once the first item is entered? | Third Round | In Review | Functionality Bug
28 | Opportunity | Yes | 4 Task Mapping | Entering item 401020 in an estimate shows description "PVC TEE S40 2" SOC x FPT" whereas the product database correctly shows "PVC TEE S40 2" SOC" | Third Round | In Review | Functionality Bug
29 | Opportunity | Yes | 4 Task Mapping | Unable to change an item by changing the item code. First step was selecting an item by entering an item code. Second step, I changed the item by using the drop down in the description. Third step, I tried to enter a new item code to change the item once more, and was unable to do so. | Third Round | In Progress | Feature Enhancement
30 | Opportunity | Yes | 4 Task Mapping | Searching for an item in the description column does not work for partial strings | Third Round | In Progress | Feature Enhancement
31 | Opportunity | Yes | 4 Task Mapping | In an estimate, deleting the last row (the one with the "Plus") will remove the "Plus" to add a row without adding it to the above row. | Third Round | Open | Feature Enhancement
36 | Opportunity | Yes | 5 Generate Estimate | The totals from step don't show up properly on this page. | Third Round | In Progress | Feature Enhancement
37 | Opportunity | Yes | 5 Generate Estimate | How is Freight adjusted? | Third Round | In Review | New Feature Addition
39 | Opportunity | Yes | 4 Task Mapping | Using the Upload CAD file, and assigning products to an estimate, the Description and Standard Cost don't update. Also, quantities have decimals, which they shouldn't | Third Round | Open | Functionality Bug
40 | Opportunity | Yes | 4 Task Mapping | Adding items accepts any input, not just products specified in the product database. This can happen via the Upload Function (see "Single-C" in screenshot) or via manual entry (see "dog" in screenshot) | Third Round | Open | Feature Enhancement
43 | Opportunity | Yes | 4 Task Mapping | How do I remove an estimate? | Third Round | In Progress | New Feature Addition
47 | Opportunity | Yes | 4 Task Mapping | All Task Codes available in drop-down | Third Round | In Review | Functionality Bug
53 | Opportunity | Yes | 4 Task Mapping | Totals not calculated for materials | Third Round | In Progress | Functionality Bug
54 | Opportunity | Yes | 5 Generate Estimate | How is tax rate adjusted? | Third Round | Open | Feature Enhancement
56 | Opportunity | Yes | 5 Generate Estimate | Combined GP is not calculated properly | Third Round | In Progress | Functionality Bug
58 | Opportunity | Yes | 5 Generate Estimate | The "S&H" column for estimates should be blank as we don't charge freight on a materials estimate level, but for the whole project | Third Round | In Progress | Feature Enhancement
59 | Opportunity | Yes | 5 Generate Estimate | Total GP is not calculated properly. Also, what is GP% indirects? | Third Round | In Progress | Functionality Bug
60 | Opportunity | Yes | 6 Proposal Creation | At this point, the selectable task codes should correspond to the rows from step 5, since we're looking for the totals of each estimate | Third Round | In Progress | Functionality Bug
61 | Opportunity | Yes | 5 Generate Estimate | Labor only estimates generated during step 5 don't show up on step 6 | Third Round | In Progress | Functionality Bug
63 | Opportunity | Yes | 6 Proposal Creation | Discuss, this screen is too clunky, in that each estimate takes up too much room. At this stage, we only need to see the task code, description, and total sell price per estimate. Also need ability to add description to each group with multiple lines / ability to add lines | Third Round | Open | Feature Enhancement
65 | Opportunity | Yes | 5 Generate Estimate | GP% - avg | Third Round | In Progress | Functionality Bug
67 | Opportunity | Yes | 7 Proposal Preview | In the proposal, we don't want to see individual tasks anymore, only the groups created in step 6 and the total $ sum of the group components. | Third Round | Open | New Feature Addition
70 | Opportunity | Yes | 7 Proposal Preview | What is Exhibit A - Project Detail? | Third Round | In Progress | Functionality Bug
71 | Opportunity | Yes | 8 Final documents | Printout needs adjustments - Exhibit A - Project detail again? - Should not show boxes around fields - Remove Trashcan Icons - page breaks need to be smart and intuitive (such as invoice on separate page , don't cut off content from header) | Third Round | Open | Feature Enhancement
76 | Opportunity | Yes | 8 Final documents | Netsuite Extract appears to show the internal ID of the task code. at this stage we need the internal ID of the parts. | Third Round | Open | Feature Enhancement

## User Bugs
Client | [6 empty] | Markman Group
ID | Proposal Application Screen | Blockers | Stage (applicable only for proposal process) | Detailed description of the issue | Screenshot | Phase | Status | Type | Comments
1 | Products |  |  | Columns: Internal ID Description Std Cost Primary Units Type Primary Stock Unit Preferred Vendor Family Type Name Parent Display Name Tax Schedule +++ supporting columns to be added to support Glue and Additional Materials calculations |  | First Round | Done | Feature Enhancement
2 | Opportunity |  | 4 Task Mapping | Comment to rename to Item Notes |  | First Round | Done | Feature Enhancement
4 | Opportunity |  | 4 Task Mapping | Add Task should have drop-down same as in the stage one, description needs to remain as users should have flexibility to name the task code as per need |  | First Round | Done | Feature Enhancement
5 | Opportunity |  | 4 Task Mapping | Material Totals are incorrect, as quantity does not play any role to calculate totals, therefore need to be corrected |  | First Round | Done | Functionality Bug
3 | Opportunity |  | 4 Task Mapping | Move lines up/down |  | First Round | Done | New Feature Addition
6 | Opportunity |  | 4 Task Mapping | Unable to deselect product, therefore blank option must be added on the top of the drop-down |  | First Round | Done | Feature Enhancement
7 | Opportunity |  | 4 Task Mapping | Description in drop-down is being off in case of long product name |  | First Round | Done | Functionality Bug
8 | Opportunity |  | 4 Task Mapping | using tab to move between columns to enter data, and also add additional line on the end |  | First Round | Done | Feature Enhancement
9 | Opportunity |  | 4 Task Mapping | search based on the Display Name (can be scoped once master table updated) |  | First Round | Done | Feature Enhancement
10 | Opportunity |  | Opportunity List | user needs to have possibility to create estimation without opportunity created |  |  | Open | Future Scope Extension (Phase 2)
11 | Opportunity |  | 5 Generate Estimate | Labour GP% & Mat.GP% - function to copy/change all rows together |  | First Round | Done | New Feature Addition
12 | Opportunity |  | 5 Generate Estimate | Total GP% - logic behin the calculation |  | First Round | Done | Functionality Bug | The Total GP% should not be calculated by simply summing up the Labor GP% and Material GP% values across tasks. Summing percentages directly does not yield a meaningful gross profit percentage for the overall document. Instead, the Total GP% should be based on aggregated dollar values, not percentages.
13 | Opportunity |  | Opportunity List | Versioning of the opportunities |  |  | Open | Future Scope Extension (Phase 2)
14 | Opportunity |  | 1 Select Task Code | Option to delete selected task |  | First Round | Done | New Feature Addition
15 | Opportunity |  | 1 Select Task Code | Description on the task-code will be editable(allign with design with Rental Application) |  | Second Round | Done | Feature Enhancement
16 | Opportunity |  | 4 Task Mapping | Description on the task-code will be editable (allign with design with Rental Application) |  | Second Round | Done | New Feature Addition
17 | Opportunity |  | 4 Task Mapping | Item Code (to be linked to Display Name Code) |  | Second Round | Done | Feature Enhancement
18 | Products |  | 4 Task Mapping | Display Name Code to be added to the master table (once implemeted above to be remapped) |  | Second Round | Done | Feature Enhancement
19 | Opportunity |  | 6 Proposal Creation | Group Description to be added (next to Group Name) Proposal to be created not on the line level but aggregated level (labor/materials) - values to be populated automatically Include: to be set-up the way, that it will either display total amount or split to labor and materials |  | Second Round | Open | Future Scope Extension (Phase 2)
20 | Opportunity |  | 7 Proposal Preview | Delete' with 'Check Box' to prevent accidental deletions. |  | Second Round | Done | Feature Enhancement
21 | Opportunity |  | 4 Task Mapping | Changing the description for an estimate on step 1 does not change the description on step 4. |  | Third Round | In Review | New Feature Rework
22 | Opportunity |  | 4 Task Mapping | Deleting an estimate on step 1 does not remove it on step 4 |  | Third Round | In Review | New Feature Rework
23 | Opportunity |  | 2 Upload CAD file | Dropping file into the "drop files here to upload" results in error "Something went wrong :( ". Same error when selecting a file through the explorer |  | Third Round | In Review | Feature Enhancement | the format should not be tmp but txt file
24 | Opportunity | No | 4 Task Mapping | Refreshing (F5) causes task codes to change order |  | Third Round | Open | Feature Enhancement | Lars to confirm if sorting is OKAY - same order on all screens (anal. + stage 4 the split between labor and notmal tasks to stay)
25 | Opportunity | Yes | 4 Task Mapping | Refreshing (F5) needs to ask for user approval before reloading the page. Any changes made to estimates appear to only be saved when going to step 5, so if the page is refreshed before moving on, all progress is lost. |  | Third Round | Open | New Feature Addition | F5 (confirmation on save)/or autosave
26 | Opportunity |  | 5 Generate Estimate | How is labor added to estimates? |  | Third Round | Done
27 | Opportunity |  | 4 Task Mapping | When entering items, can we make the description field as large as possible from the beginning, and not only once the first item is entered? |  | Third Round | In Porgress | Feature Enhancement
28 | Opportunity |  | 4 Task Mapping | Entering item 401020 in an estimate shows description "PVC TEE S40 2" SOC x FPT" whereas the product database correctly shows "PVC TEE S40 2" SOC" |  | Third Round | In Porgress | Functionality Bug | check the mapping between item code & description - vs product master
29 | Opportunity |  | 4 Task Mapping | Unable to change an item by changing the item code. First step was selecting an item by entering an item code. Second step, I changed the item by using the drop down in the description. Third step, I tried to enter a new item code to change the item once more, and was unable to do so. |  | Third Round | Open | Feature Enhancement | already added rows allowed to change description/item code - should be availabel for active row
30 | Opportunity |  | 4 Task Mapping | Searching for an item in the description column does not work for partial strings |  | Third Round | In Porgress | Feature Enhancement | cross check (similar to NetSuite)
31 | Opportunity |  | 4 Task Mapping | In an estimate, deleting the last row (the one with the "Plus") will remove the "Plus" to add a row without adding it to the above row. |  | Third Round | Open | Feature Enhancement
32 | Opportunity |  | 4 Task Mapping | Unable to change the order of items within an estimate. We want to be able to drag items up/down within an estimate, and also select / multi select items to be able to copy / paste them into other estimates, possibly other opportunities |  | Third Round | Open | Future Scope Extension (Phase 2) | bulk movements of the rows
33 | Opportunity |  | 4 Task Mapping | Add functionality to add group of items to an estimate |  | Third Round | Open | Future Scope Extension (Phase 2) | having option to create groups of materials to select for task mapping
34 | Opportunity | No | 4 Task Mapping | For each estimate, the $total does not update when adding parts. Also, estimates don't need columns for Quantity, Units, unit Price |  | Third Round | Open | Feature Enhancement | autosave
35 | Opportunity |  | 4 Task Mapping | Vendor list is incomplete |  | Third Round | Done |  | Mark to sent complete Vendor List
36 | Opportunity | Yes | 5 Generate Estimate | The totals from step don't show up properly on this page. |  | Third Round | Open | Feature Enhancement | not unit price, confirmation pending
37 | Opportunity |  | 5 Generate Estimate | How is Freight adjusted? |  | Third Round | In Review | New Feature Addition | should be to Task Mapping (and set-up as regular task code --) - the product list should be expanded to see noninventory items --- S&H
38 | Opportunity |  |  | Locking Proposals in Edit Mode |  | Third Round | Open | Future Scope Extension (Phase 2)
39 | Opportunity | Yes | 4 Task Mapping | Using the Upload CAD file, and assigning products to an estimate, the Description and Standard Cost don't update. Also, quantities have decimals, which they shouldn't |  | Third Round | Open | Functionality Bug | tmp file used
40 | Opportunity |  | 4 Task Mapping | Adding items accepts any input, not just products specified in the product database. This can happen via the Upload Function (see "Single-C" in screenshot) or via manual entry (see "dog" in screenshot) |  | Third Round | Open | Feature Enhancement | how the not valid codes are being validated with Upload CAD no valid items should not be populated in the estimate - but should be visible under 'non valid parts' - in assign parts
41 | Opportunity | No | 2 Upload CAD file | .tmp file cause an error when trying to upload. The file is loaded into one drive -> AutoCAD files -> "Upload Test - Caused Error.tmp". I could not identify a significant difference to the file accepted by the system ("CAD EXPORT.Tmp") |  | Third Round | Open | Functionality Bug | incorrect file type as QUANTITY is **** therefore giving error (edge case) if not number replace by zero
42 | Opportunity | No | 4 Task Mapping | Regarding linking Labor estimates to other Estimates, when estimates are collapsed, can we show: 1. On the labor estimate, show which material estimate it is linked to 2. On the material estimate, show which labor estimate is linked to it (if any) |  | Third Round | Open | New Feature Addition | instead of unit price etc./show linked labor/or task code
43 | Opportunity | Yes | 4 Task Mapping | How do I remove an estimate? |  | Third Round | Open | New Feature Addition
44 | Opportunity | No | 4 Task Mapping | Linking a labor estimate to a material estimate refreshes the page, removing any items entered on the material or labor side. We already addressed this for manually refreshing the page, but the linkage between labor and materials needs to work without refreshing then? |  | Third Round | Open | Feature Enhancement
45 | Opportunity | No | 4 Task Mapping | Can we make it more visible when the delete or add button are highlighted? This applies to when tabbing through the line, it's hard to see which one is currently highlighted |  | Third Round | Open | Feature Enhancement
46 | Opportunity |  | 4 Task Mapping & 5 Generate Estimate | Added labor and linked to estimates, but it doesn't show up in step 5 |  | Third Round | Done
47 | Opportunity | Yes | 4 Task Mapping | All Task Codes available in drop-down |  | Third Round | Open | Functionality Bug
48 | Opportunity |  | 4 Task Mapping | Auto-refresh |  | Third Round | Open | Feature Enhancement | annoying
49 | Products | Yes |  | Attempting to modify the glue / additional material calculator, and I can't find where to do that. I imagine it would be in the Products -> Additional Material tab? |  | Third Round | Open | Feature Enhancement
50 | Opportunity | No | Any | I believe we talked about this already, but any time the page refreshes, it loads the last used stage, instead of remaining on the page I'm on. For example I'm assigning parts to estimates during stage 4, but after every assign it loads to the last used stage. |  | Third Round | Open | Feature Enhancement
51 | Opportunity | No | 4 Task Mapping | When assigning parts from a file upload, it's currently possible to keep assigning the same parts to estimates. Once parts are assigned, they should drop off the assign list or move to a section of "Already assigned" |  | Third Round | Open | Feature Enhancement
52 | Opportunity | No | 4 Task Mapping | When assigning parts from a file upload, the parts should show up in order by the part number. |  | Third Round | Open | Feature Enhancement
53 | Opportunity | Yes | 4 Task Mapping | Totals not calculated for materials |  | Third Round | Open | Functionality Bug
54 | Opportunity | Yes | 5 Generate Estimate | How is tax rate adjusted? |  | Third Round | Open | Feature Enhancement | changable
55 | Opportunity | No | 5 Generate Estimate | "Mat. Cost" column is part of materials section |  | Third Round | Open | Feature Enhancement
56 | Opportunity | Yes | 5 Generate Estimate | Combined GP is not calculated properly |  | Third Round | Open | Functionality Bug
57 | Opportunity | No | 5 Generate Estimate | Once you enter "View full Table" view, there is no back button. using the back button of the browser works, but there should be a dedicated button |  | Third Round | Open | Feature Enhancement | View Table purple button
58 | Opportunity | Yes | 5 Generate Estimate | The "S&H" column for estimates should be blank as we don't charge freight on a materials estimate level, but for the whole project |  | Third Round | Open | Feature Enhancement | not editable (remove) - total of F.
59 | Opportunity | Yes | 5 Generate Estimate | Total GP is not calculated properly. Also, what is GP% indirects? |  | Third Round | Open | Functionality Bug | calc logic - for each box
60 | Opportunity | No | 6 Proposal Creation | At this point, the selectable task codes should correspond to the rows from step 5, since we're looking for the totals of each estimate |  | Third Round | Open | Functionality Bug | Mat,Tax,Labor
61 | Opportunity | Yes | 5 Generate Estimate | Labor only estimates generated during step 5 don't show up on step 6 |  | Third Round | Open | Functionality Bug | labor estimates vs material and labor estimate
62 | Opportunity | No | 6 Proposal Creation | after creating the group, there's a trash can icon per estimate, which I believe simply removes the estimate from the group to be re-assigned to another group (which is a necessary feature and good). Let's rephrase the pop-up from "Are you sure you want to delete ****" to "Are you sure you want to remove *** from group?" |  | Third Round | Open | Feature Enhancement
63 | Opportunity | Yes | 6 Proposal Creation | Discuss, this screen is too clunky, in that each estimate takes up too much room. At this stage, we only need to see the task code, description, and total sell price per estimate. Also need ability to add description to each group with multiple lines / ability to add lines |  | Third Round | Open | Feature Enhancement | description to only group/not task - remove the items
64 | Opportunity | No | 6 Proposal Creation | Opposite ability to two rows above, want to be able to add estimates to a group |  | Third Round | Open | Feature Enhancement | to existing group add task code -
65 |  | Yes | 5 Generate Estimate | GP% - avg |  | Third Round | Open | Functionality Bug
66 | Opportunity | No | 7 Proposal Preview | How are estimates designated as options? Currently all estimates are listed as options, which is incorrect. |  | Third Round | Open | Feature Enhancement | check on estimate (option/not option)
67 | Opportunity | Yes | 7 Proposal Preview | In the proposal, we don't want to see individual tasks anymore, only the groups created in step 6 and the total $ sum of the group components. |  | Third Round | Open | New Feature Addition
68 | Opportunity | No | 7 Proposal Preview | These fields should not be manual entry |  | Third Round | Open | New Feature Addition | import from Netsuit
69 | Opportunity | No | 7 Proposal Preview | This is one text, not multiple lines. One would never unselect one line individually. |  | Third Round | Open | Feature Enhancement | SALES AND APPROVAL AGREEMENT - always there and editable
70 | Opportunity | No | 7 Proposal Preview | What is Exhibit A - Project Detail? |  | Third Round | Open | Functionality Bug | check - not needed
71 | Opportunity | Yes | 8 Final documents | Printout needs adjustments - Exhibit A - Project detail again? - Should not show boxes around fields - Remove Trashcan Icons - page breaks need to be smart and intuitive (such as invoice on separate page , don't cut off content from header) |  | Third Round | Open | Feature Enhancement
72 | Opportunity | No | 7 Proposal Preview | Create master check box for pump installation terms to disable all |  | Third Round | Open | Feature Enhancement
73 | Opportunity | No | 8 Final documents | Print file name adjustment to include opportunity number |  | Third Round | Open | Feature Enhancement
74 | Opportunity | No | 8 Final documents | I don't understand what "New Material Master Data" is supposed to tell me, it includes labor and all items from the opportunity |  | Third Round | Open | Feature Enhancement | check
75 | Opportunity | No | 8 Final documents | I don't understand what "Cost Variance" is supposed to tell me |  | Third Round | Open | Feature Enhancement | more clear structure - pause
76 | Opportunity | Yes | 8 Final documents | Netsuite Extract appears to show the internal ID of the task code. at this stage we need the internal ID of the parts. |  | Third Round | Open | Feature Enhancement

## DropDowns (hidden)
Rental Application Screen | Stage | Status | Type
Opportunity | Opportunity List | Open | Functionality Bug | Issues within the agreed scope that impact the application’s functionality and need fixing.
Products | 1 Select Task Code | In Porgress | Feature Enhancement | Requests to improve or extend existing features, adding value without introducing new functionality.
Labour Cost | 2 Upload CAD File | In Review | New Feature Addition | Requests for entirely new features not included in the original scope or prototype.
Customers | 3 Material List | Done | Future Scope Extension (Phase 2) | Significant adjustments or expansions that will be scheduled for a later phase due to resource and time considerations.
Tasks | 4 Task Mapping |  | New Feature Rework | This category encompasses issues found in newly implemented features that require debugging, corrections, or rework to function as expected according to the original requirements.
Vendors | 5 Generate Estimate
Authorization | 6 Proposal Creation
7 Proposal Preview
8 Final Documents