## Feedbacks
Client |  |  |  |  | Markman Group
ID | Rental Application Screen | Stage (applicable only for rental process) | Detailed description of the issue | Screenshot | Status | Type | Comments
1 | Master Data | Account Managers | Add only our current account managers |  | Done | Master Data Update | NN: needs update once all master data received.
2 | Rent Process | Create Order | Need to add base price to all rental items |  | Open | Change Request
3 | Rent process | Create Order | Rental Period: Need a description of how this operates. Select start day and end day? |  | Open | Question | NN: SOP needs update on explanation of how to use 'Rental Period'
4 | Rent process | Create Order | only accepts whole numbers - needs to allow two digits past decimal ie: 8.99 |  | Done (not deployed) | Configuration Update
5 | Rent process | Create Order | Customer email - this needs to be the rental contact at the customer |  | Open | Master Data Update | NN: needs update once all master data received (rental conact = customer email).
6 | Rent Process | Create Order | Pick-up location: needs to have address and map option. The case will be that at times we will move from a farm location to another farm location |  | Open | Change Request
7 | Rent process | Create Order | If i put a quantity in the order that goes over what is available it will not accept the item at all. Need to be able to input order and have their be awareness that we do not have stock vs stopping the process. |  | Open | Change Request | NN: backorder implementation.
8 | Rent Process | Create Order | It is common to deliver to a customer what they originally believe the need and then a week or two later exchange/accept return on items due to scope change or change in point of connection. How do we address this in the system? |  | Open | Change Request | NN: price adjustment on the order.
9 | Rent Process | Create Return Delivery | What happens when we move a portion of pipe at end of rental from customer A to customer B. Can we leave some pipe at customer A? |  | Open | Change Request | NN: it should populate at Stock Reporting as new inventory location 'field stored' - when with customer after rental period.
10 | Rent Process | Create Return Delivery | Our overall objective at time is to leave the 3" pipe on the growers site and return to inventory/send to another job the 10" mainline and accessory parts. Is this easy to do? |  | Open | Change Request | NN: it should populate at Stock Reporting as new inventory location 'field stored' - when with customer after rental period (duplication of point 10).
11 | Master Data | Customers | This should only be the list of customers for rental that was provided |  | Done | Master Data Update | NN: needs update once all master data received.
12 | Rent Process | Pricing | Price per unit per rental period is how we think about pricing...how do we show this at time of order entry on the line item? |  | Open | Change Request | NN: TBD and clarify on customer side.
13 | Master Data | Products | Eliminate all but rental products |  | Done | Master Data Update | NN: needs update once all master data received.
14 | Master Data | Warehouse | Elminate all but Laurel warehouses |  | Done | Master Data Update | NN: needs update once all master data received.
15 | Master data | Warehouse | How will the system handle pipe that we store at a growers location when it is not on rental? |  | Open | Change Request | NN: it should populate at Stock Reporting as new inventory location 'field stored' - when with customer after rental period (duplication of point 10).
16 | Master data | Warehouse Rental List | Need to agree on a process that will allow full inventory or bogus number to be put in the system at beginning so we do not run into issue with no stock being available when trying to create new rentals |  | Done | Question | QQ: Stock Adjustment screen.
17 | Rent process | Water Source | Select from: well, canal, resevoir, district turnout, other |  | Open | Change Request
18 | Home | Map | Warehouses should always be populated there, but for customers - customer pin should be visible on the map only in case they have active order with us (basically if order exists for customer, you will have customer pin there). |  | Done (not deployed) | Configuration Update | entered by Markman Group as per feedback during meeting
19 | Home | Map | Customer location pin should be populated from the PIN location (delivery location) on the delivery not from the billing address from master data. |  | Open | Change Request | entered by Markman Group as per feedback during meeting
20 | Reports | Report | Validation of quantities - we must have report additional one, that will show us Equipment A, we own 100 of it, 50 is with customer and 50 is in the warehouse. |  | Open | Change Request | entered by Markman Group as per feedback during meeting
21 | Rent Process | Add new rental stage | End of Rental/Stored at Customer Location |  | Open | Change Request | NN:Option to mark it in rental process so it will be available in inventory.
22 | ??? | Inventory Status | For items that are field stored, we do inspect pipe at end of rental. I believe we have requested a status when we receive product that is Out of Service. We will field inspect and most likely move product to Out - of - Service as well. How do we address this? |  | Open | Change Request | NN: backorder implementation (duplication of point 8).
23 | Rent Process | Product | It is comment to deliver what was ordered to a customer and in the following 2-3 weeks when they begin deploying the equipment in the field have the customer need additional items due to changes in field layout/conditions. In some cases we are adding equipment, we also can get returns or both add and returns. We need to be able to make adjustments to the order when this occurs. |  | Open | Change Request | NN: backorder implementation (duplication of point 8).
24 | Rent Process | Rental return | There are times when we "Field Store" pipe at a growers location after the rental is complete. Very common for accessory items to be returned to Laurel warehouse when this occurs. Is the system setup to do this? |  | Open | Change Request | NN: it should populate at Stock Reporting as new inventory location 'field stored' - when with customer after rental period (duplication of point 10).
25 | Reports | Reports | When we have items we can fill in an order is there a backorder report that show this? |  | Open | Change Request | NN: backorder implementation.
26 | Application itselft |  | How does rental app sync with NetSuite? |  | Done | Question | QQ: Mark proposed to reused already available solution/tool that is being leveraged at this moment.
27 | Rent process | Create Return Delivery | It appears we can't create a return/pickup prior to rental period being over. We do have rental periods change. How address? |  | Done | Question | NN: You can create 'Return Delivery' only once stage 'Delivered to Customer' is completed.

## DropDowns
Status | Type
Open | Master Data Update
In Porgress | Functionality Bug
In Review | Configuration Update
Done | Change Request
Done (not deployed) | Question