Metropolitan Data and Reporting

Proposal for Quick Wins

MARKMAN GROUP

Contents

Metropolitan DealCloud usage optimization project	3

Project Overview	3

Data Governance (in parallel)	3

1.	Current DealCloud Usage Assessment (Led by Metropolitan)	3

2.	Future process and requirements (Led by Metropolitan)	4

In Question if included in Governance or SOW Phase II	8

3.	Deal Cloud Customization	8

4.	Metropolitan Data Architecture Technical Setup (optional)	9

5.	Data Quality monitoring & Reporting Dashboard	10

6.	Automated email notifications	11

7.	Training & Change Management	12

Proposal Summary	12

Scope Assumptions	13

Team, Effort and Pricing	13

Timeline	14

Deal Cloud – Pipeline and Funnel Dashboards	16

Roles & Responsibilities	17

Team, Effort and Pricing	17

Timeline	18

Visualization of PIPE via PowerBI	19

Project Overview	19

Scope Assumptions:	19

Roles & Responsibilities	19

Team, Effort and Pricing	19

Timeline	19

Combined Project Approach	19

# Metropolitan DealCloud usage optimization project

## Project Overview

This project focuses on optimizing the usage of DealCloud within the firm to enhance data quality, streamline processes, and improve overall efficiency across teams. The primary goal is to define and implement optimal workflows, introduce effective data governance practices, and ensure DealCloud is utilized to its full potential.

Our group will support the initiative by providing technical expertise and guidance, helping to implement solutions efficiently while assisting with key activities such as data integration, automation, and reporting. The objective is to deliver quick wins early in the process, enabling the firm to experience immediate benefits, such as reducing manual effort, improving data accuracy, and supporting users in maintaining high data quality.

Additionally, this project will serve as a foundation for demonstrating the benefits of a structured data management approach. It will act as a proof of concept for applying similar principles to broader data architecture initiatives in the future, showcasing how optimized data processes and infrastructure can drive efficiency and value across the organization.

To ensure a structured and efficient optimization of DealCloud usage, we propose approaching the project in seven key stages.

# Data Governance (in parallel)

### Current DealCloud Usage Assessment (Led by Metropolitan)

This phase focuses on consolidating and documenting the current state of DealCloud usage within the firm. The firm has already undertaken a separate project to map and optimize key DealCloud processes. Additionally, initial assessments have been conducted through joint review sessions with Markman Group, identifying key processes, user interactions, and data flows.

The objective of this phase is to organize and integrate all existing insights, filling any gaps to ensure a comprehensive understanding of how DealCloud is currently utilized across teams. To maximize efficiency, it is recommended that the firm leads this effort, with our group providing support as needed to ensure a structured and thorough approach.

By systematically capturing all relevant information, we aim to create a clear baseline that will serve as a foundation for the next phase of process optimization. This structured approach ensures that no critical elements are overlooked, enabling more effective planning and implementation in the subsequent stages of the project.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Markman Group | Metropolitan |
| --- | --- | --- | --- | --- |
| 1.1 | Identify DealCloud Data Fields & Structure | Detailed Data Inventory Document (fields, data types, usage) | Consulted | Responsible |
| 1.2 | Identify Data Ownership & Responsibilities | Data Ownership Matrix (RACI) | Consulted | Responsible |
| 1.3 | Assess Data Quality & Current Issues | Data Quality Assessment Report (gaps, inconsistencies, issues) | Responsible | Accountable |
| 1.4 | Review Current DealCloud Customizations | Customization Inventory (workflows, forms, automations) | Consulted | Responsible |
| 1.5 | Analyze Current Integration Points | Integration Map (API connections, manual data flows) | Responsible | Accountable |
| 1.6 | Identify Reporting & Dashboard Requirements | List of Current Reports/Dashboards & their Data Dependencies | Accountable | Responsible |

### Future process and requirements (Led by Metropolitan)

In this phase, Metropolitan, with support from our group, will define the optimal future processes for DealCloud usage. The focus will be on outlining clear workflows, data requirements, and the specific fields necessary to support efficient operations across teams. To ensure sustainability and accountability, we recommend introducing key data governance roles that have been jointly identified, such as Data Stewards, Data Owners, and the DealCloud Support Team.

Additionally, this phase will clearly establish the coordination framework, detailing responsibilities for each party involved:

- Metropolitan will lead the process definition, decision-making, and adoption of best practices.

- Our group will provide guidance, technical expertise, and support to ensure the process design aligns with data management and automation capabilities.

- The DealCloud Support Team will assist with platform-specific adjustments and ensure that system configurations reflect the newly defined workflows.

This collaborative approach will ensure that DealCloud processes are efficient, scalable, and aligned with Metropolitan’s strategic objectives.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Markman Group | Metropolitan |
| --- | --- | --- | --- | --- |
| 2.1 | Define Target Operating Model for DealCloud Usage | Target Operating Model Document (how each team should use DealCloud) | Consulted | Responsible |
| 2.2 | Design Optimized Workflows for Each Team | Workflow Diagrams (Deal Team, IR, Asset Management, etc.) | Consulted | Responsible |
| 2.3 | Standardize Data Fields & Structures | Data Field Dictionary (standardized fields, formats, mandatory fields) | Consulted | Responsible |
| 2.4 | Define Roles & Responsibilities (RACI) | RACI Matrix (Data Owners, Data Stewards, DealCloud Support Team) | Consulted | Responsible |
| 2.5 | Establish Data Governance Framework | Data Governance Policy Document (roles, data stewardship processes) | Responsible | Accountable |
| 2.6 | Develop Data Quality Management Process | Data Quality Framework (validation rules, data checks, issue resolution process) | Responsible* | Responsible* |
| 2.7 | Onboard Asset Management Team to DealCloud | Asset Management Onboarding Plan | Consulted | Responsible |
| 2.8 | Define Reporting & Dashboard Strategy | Reporting Framework (standard reports, dashboards, KPIs to track) | Accountable | Responsible |

*Metropolitan is responsible for aligning and designing process and Markman Group is responsible for developing the compliance check and rules.

Key roles definition:

- Data Owner

Summary:
The Data Owner holds ultimate accountability for the quality, integrity, and security of specific data sets. They make decisions about data usage, access rights, and compliance with organizational policies.

Main Responsibilities:

- Define data ownership boundaries and responsibilities.

- Define data quality checks and validation rules.

- Approve data management policies and procedures.

- Ensure data complies with legal, regulatory, and business requirements.

- Prioritize data-related issues and initiatives.

- Provide final sign-off on data quality improvements.

- Data Steward

Summary:
The Data Steward is responsible for the day-to-day management of data. They ensure data accuracy, consistency, and completeness through continuous monitoring, validation, and coordination with data users.

- Main Responsibilities:

- Monitor data quality and flag discrepancies or issues.

- Implement data quality checks and validation rules.

- Work with data owners to correct and prevent data issues.

- Maintain data documentation, definitions, and standards.

- Support data audits and compliance activities.

- Process Owner

Summary:
The Process Owner is responsible for defining, managing, and optimizing business workflows that generate or consume data. They ensure processes are aligned with business objectives and that data flows efficiently within these processes.

Main Responsibilities:

- Design and document workflows related to DealCloud usage.

- Define data entry requirements for each process stage.

- Identify process bottlenecks and implement improvements.

- Ensure process adherence across teams.

- Collaborate with Data Owners and Stewards for data-driven process improvements.

- Data Governance Lead

Summary:
The Data Governance Lead oversees the entire data governance framework. They ensure that data policies, standards, and procedures are consistently applied across the organization.

Main Responsibilities:

- Develop and maintain data governance policies and standards.

- Coordinate data governance activities across departments.

- Facilitate data governance meetings and workshops.

- Ensure alignment with regulatory and compliance requirements.

- Promote data governance awareness and best practices.

- Technical Support / Data Engineer

Summary:
The Data Engineer is responsible for the technical implementation of data processes, including API integrations, data pipelines, automation workflows and quality dashboard.

Main Responsibilities:

- Develop and maintain APIs for data extraction from DealCloud

- Build data pipelines for data transformation and loading into data storage systems (e.g., Azure).

- Automate data quality monitoring and notification systems

- Build Quality Dashboard for monitoring

- Ensure system performance, scalability, and security.

- Troubleshoot technical issues and support users.

- Business Analyst

Summary:
The Business Analyst acts as a bridge between business teams and technical teams. They gather requirements, analyze data, and help translate business needs into technical solutions.

Main Responsibilities:

- Gather and document business requirements for DealCloud optimization.

- Analyze current data flows and identify gaps or inefficiencies.

- Propose improvements based on data analysis and stakeholder feedback.

- Facilitate communication between business and technical teams.

- Support testing and validation of new features or data processes.

- Compliance & Risk Officer (Optional)

Summary:
The Compliance & Risk Officer ensures that data management activities adhere to legal, regulatory, and internal compliance standards. They focus on data privacy, security, and risk mitigation.

Main Responsibilities:

- Review data handling practices for compliance with regulations (e.g., GDPR, data privacy laws).

- Conduct periodic audits and risk assessments.

- Provide guidelines on data security and access controls.

- Collaborate with Data Governance Lead on compliance-related policies.

- Address data breaches or compliance incidents promptly.

| Role | Responsibility | Suggested Candidates |
| --- | --- | --- |
| Data Owner | Overall data accountability | Department Heads |
| Data Steward | Day-to-day data quality management | Markman Group |
| Process Owner | Define and optimize business workflows | Stephen & Team Leads |
| Data Governance Lead | Oversee data governance framework | Stephen and Markman Group ??? |
| DealCloud Technical Support | System configuration | DealCloud support team |
| Technical Support | API integration, automation, data pipelines | Markman Group |
| Business Analyst | Bridge business requirements and data | Business Analyst from each team |
| Compliance & Risk Officer | Regulatory compliance and data audits | Compliance Officer |

# In Question if included in Governance or SOW Phase II

### Deal Cloud Customization

The DealCloud Customization phase focuses on implementing system changes to align the platform with the firm’s defined workflows, data requirements, and business processes. Based on the future-state design, the DealCloud Support Team will configure and optimize the platform to ensure it effectively supports the needs of all teams. This includes setting up new fields, defining mandatory data entry criteria, and establishing workflows that promote data consistency and process efficiency.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Markman Group | Metropolitan | DealCloud |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Review Future State Requirements | Customization Requirements Document (based on optimized workflows and data governance) | Informed | Responsible | Consulted |
| 3.2 | Gap Analysis Between Current Setup and Desired State | Gap Analysis Report (identifies what needs to be added, removed, or changed) | Informed | Responsible | Consulted |
| 3.3 | Configure Data Fields & Structures | Updated DealCloud Data Model (new fields, modified field types, standardized formats) | Informed | Accountable | Responsible |
| 3.4 | Customize Workflows & Automations | Configured Workflows (stage-specific workflows, task automation within DealCloud) | Informed | Accountable | Responsible |
| 3.5 | Implement Role-Based Access Controls | Updated Access Permissions (aligned with the data governance framework) | Informed | Responsible | Responsible |
| 3.6 | Testing & User Acceptance | UAT Test Plans & Results (ensures changes meet business needs and workflows function correctly) | Informed | Responsible | Accountable |
| 3.7 | Documentation of Changes | System Configuration Documentation (details of all customizations for future reference) | Informed | Accountable | Responsible |
| 3.8 | User Training on New Features | Training Materials & Sessions (focused on new workflows, fields, and dashboards) | Informed | Responsible | Consulted |

### Metropolitan Data Architecture Technical Setup (optional)

During this phase Markman Group will establish the technical foundation in alignment with the proposed data architecture. By focusing initially on DealCloud, we reduce complexity while setting up a scalable framework that can be expanded to other systems in the future.

The primary objective of this phase is to create a robust data pipeline that enables near real-time data availability. To achieve this, we will implement APIs for seamless data integration between DealCloud and the Azure data environment. As part of this process, we will also review the firm's current DealCloud subscription to assess existing API capabilities and determine if any additional configurations or upgrades are required.

This technical setup ensures data can flow efficiently from DealCloud into the centralized architecture, supporting advanced reporting, analytics, and automation while laying the groundwork for future data initiatives.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Responsible |
| --- | --- | --- | --- |
| 4.1 | Define Technical Requirements | Technical Requirements Document (API integration, data flow, reporting needs) | Markman Group |
| 4.2 | Design Data Architecture (PoC) | Architecture Blueprint (API → Data Lake → SQL Database) |  |
| 4.3 | API Integration Setup | Established API Connection to DealCloud (automated data extraction process) |  |
| 4.4 | Data Ingestion into Azure Data Lake | Automated Data Ingestion Pipeline (structured raw data from DealCloud) |  |
| 4.5 | Set Up Azure SQL Database | Configured SQL Database Environment (ready for curated data storage) |  |
| 4.6 | Configure Data Integration Orchestration (ADF) | Automated Data Flow Setup (schedule data pulls and manage workflows) |  |
| 4.7 | Technical Testing & Validation | Verified Data Flow, API Connection, and Storage Integrity |  |

(*) We believe a data lake POC would be beneficial in showcasing the solution's capabilities. However, if deemed unnecessary at this stage, we can proceed without it.

### Data Quality monitoring & Reporting Dashboard

Markman Group will develop a comprehensive solution to monitor and improve the quality of data within DealCloud. This phase aims to provide clear visibility into data hygiene, enabling proactive management and timely resolution of data issues.

To ensure quick delivery and immediate value, the dashboard development will not be dependent on the Azure SQL Database setup. We will initially build the solution using direct data exports from DealCloud, following an agile approach to deliver early results. Once the Azure environment is fully established, the data connection will seamlessly switch to the SQL Database, ensuring smooth continuity without disrupting user experience.

We will design and implement a Power BI dashboard that visualizes key data quality metrics, such as missing fields, outdated records, and inconsistencies. By defining critical KPIs and incorporating drill-down features, the dashboard will allow users to identify data gaps and track progress over time.

This dashboard will support data governance efforts and serve as a valuable tool for business users, providing actionable insights to maintain data accuracy and consistency across DealCloud while enabling early benefits before the full data architecture is in place.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Markman Group | Metropolitan |
| --- | --- | --- | --- | --- |
| 5.1 | Design Power BI dashboard to visualize data quality metrics | Dashboard Wireframes and Design Specifications | Responsible | Accountable |
| 5.2 | Connect Power BI to Azure SQL Database for real-time monitoring | Established Data Connection for Live Data Feeds |  |  |
| 5.3 | Define dashboard KPIs (e.g., missing data fields, outdated records) | Documented List of Data Quality KPIs |  |  |
| 5.4 | Develop data quality report with drill-down features | Interactive Power BI Report with Drill-Down Capabilities |  |  |

### Automated email notifications

The Markman Group will design and implement an automated notification system to enhance data quality maintenance within DealCloud. The goal is to create an efficient feedback loop that proactively informs users about data issues, driving timely updates and reducing manual follow-ups.

To accelerate delivery and provide immediate value, this automation will not rely on the Azure SQL Database setup. We will initially build the notification workflows using direct data exports from DealCloud, allowing us to deliver quick wins. Once the Azure environment is fully operational, the automation will seamlessly transition to leverage the SQL Database without disrupting the process.

We will develop workflows that automatically identify data quality issues, such as missing fields, outdated information, or inconsistent entries. The system will send personalized email notifications to each responsible user, consolidating all required updates into a single, easy-to-navigate message. These emails will include direct links to the relevant DealCloud records, maximizing efficiency and minimizing the time users spend searching for data to correct.

This phase will significantly improve the data cleansing process, reduce manual effort, and help maintain high data quality standards, ensuring that users receive clear, actionable tasks tailored to their responsibilities.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Markman Group | Metropolitan |
| --- | --- | --- | --- | --- |
| 6.1 | Design KNIME workflows to identify data quality issues automatically | KNIME Workflow Design Documents | Responsible | Accountable |
| 6.2 | Set up automated email notifications for data owners with pending data issues | Automated Notification System for Data Quality Alerts |  |  |
| 6.3 | Schedule regular KNIME jobs for continuous monitoring | Scheduled KNIME Jobs for Automated Data Quality Checks |  |  |
| 6.4 | Test automation workflows to ensure timely and accurate notifications | Test Results and Adjusted KNIME Workflows |  |  |

### Training & Change Management

Markman Group will provide targeted training to help users effectively work with the new data quality dashboard and automated email notifications. We will also deliver technical documentation for all implemented processes to support ongoing use. This phase ensures users are comfortable with the tools and processes, with continued support available as needed.

The table below outlines key activities, expected outputs, and responsible parties for this phase to ensure clear accountability and efficient execution.

| Nr. | Task | Output | Markman Group | Metropolitan |
| --- | --- | --- | --- | --- |
| 7.1 | Develop user training materials for new workflows and dashboards | Training Manuals & Guides | Responsible | Accountable |
| 7.2 | Conduct training sessions for DealCloud users and data stewards | Training Sessions |  |  |
| 7.3 | Provide documentation for API workflows and dashboard usage | Technical Documentation for APIs, Dashboards, and Processes |  |  |
| 7.4 | Post-implementation support | Defined Support Channels |  |  |

## Proposal Summary

With the proposed approach, Metropolitan will gain a streamlined, efficient, and future-ready data environment that supports both day-to-day operations and strategic decision-making. A better-defined process, supported by optimized DealCloud usage, will improve data accuracy, reduce manual efforts, and enhance cross-team collaboration.

The introduction of data governance, along with automation and reporting tools, will ensure consistent data standards, clear ownership, and long-term sustainability of data quality. This framework will help the firm not only maintain cleaner data but also drive accountability across teams.

Key value drivers and benefits of the project include:

- Quick Wins & Early Deliveries:

  - Data Quality Dashboard: Provides immediate visibility into data hygiene issues, enabling fast identification and resolution.

  - Automated Email Notifications: Personalized reminders for users to efficiently manage and cleanse data, reducing manual follow-ups.

- Improved Data Accuracy & Governance:

  - Automated validation checks and monitoring tools to reduce errors.

  - Clearly defined roles and responsibilities to ensure data ownership and accountability.

- Increased Process Efficiency:

  - Automation of repetitive tasks, freeing up time for strategic activities.

  - Streamlined workflows reducing manual interventions in data management.

- Enhanced Reporting & Insights:

  - Simplified data flows into tools like Power BI and KNIME for faster, more reliable reporting.

  - Near real-time data updates through API integrations with Azure Data Lake.

- Future-Ready Data Architecture:

  - Serves as a proof of concept for broader data architecture improvements.

  - Scalable foundation that supports advanced analytics, including AI/ML capabilities in the future.

## Scope Assumptions

- It is assumed that the data collection activities for Phases 1 and 2 have been progressed already by Metropolitan, thereby reducing the overall project timeline.

- Markman Group will develop training materials related to development performed. Metropolitan will handle DealCloud process training.

- The dashboard will visualize data quality workflows and metrics identified during Phases 1 and 2, using only data from DealCloud.

- In Phases 1 and 2, for those activities where Markman Group acts in a consultative role, we´ll provide guidance on necessary information and formats, but not attending sessions. Session attendance can be included for an additional fee.

- Metropolitan will host the solution on their infrastructure and cover associated costs (e.g., PowerBI licenses). Solution maintenance is excluded from the scope.

## Team, Effort and Pricing

| Phases | Markman Group Team | Estimated Hours | Pricing | TOTAL |
| --- | --- | --- | --- | --- |
| Current DealCloud Usage Assessment | Business Analyst | 40 | $150/hr | $6,000 |
| Future process and requirements | Business Analyst | 40 | $150/hr | $6,000 |
| DealCloud Customization | N/A | 0 | - | - |
| Metropolitan Data Architecture Technical Setup | Data Engineer | 80* | $200/hr | $16,000 |
| Data Quality monitoring & Reporting Dashboard | PowerBI Developer | 60 | $180/hr | $10,800 |
| Automated email notifications | Automation Developer | 16 | $180/hr | $2,880 |
| Training & Change Management | Business Analyst | 16 | $150/hr | $2,400 |
| Overall | Project Manager | 16 | $200/hr | $3,200 |
| TOTAL |  | 252 hours |  | $47,280 |

*If simpler architecture is selected the number of hours on Data Engineer will be reduced accordingly.

## Timeline

| Phases* | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Current DealCloud Usage Assessment * |  |  |  |  |  |  |  |  |
| Future process and requirements |  |  |  |  |  |  |  |  |
| DealCloud Customization |  |  |  |  |  |  |  |  |
| Metropolitan Data Architecture Technical Setup |  |  |  |  |  |  |  |  |
| Data Quality monitoring & Reporting Dashboard |  |  |  |  |  |  |  |  |
| Automated email notifications |  |  |  |  |  |  |  |  |

*The project timeline is primarily driven by Markman Group's tasks. However, activities dependent on Metropolitan or DealCloud could impact the overall project duration.

The first two phases are contingent upon work already completed by Metropolitan and their specific requirements.

DealCloud customization falls under the responsibility of Metropolitan and DealCloud, and they should determine the effort required. Certain activities, such as automated email notifications, are dependent on the completion of this customization phase.

# Deal Cloud – Pipeline and Funnel Dashboards

The Deal Team generates, validates, and distributes reports to provide stakeholders with comprehensive insights into deal pipeline activity, decision-making processes, and strategic outcomes. These reports cater to internal teams, senior management, and external stakeholders such as investors. This phase is focused on automating 2 reports prepared by the Deal Team (Pipeline and Funnel). These reports leverage data primarily from Deal Cloud, supplemented by manual inputs, to ensure clarity, consistency, and alignment with business objectives.

Objective: To transform and automate the creation of two of the reports delivered by Deal Team (Pipeline and Funnel). The goal of this phase is to enhance efficiency and reduce manual effort in report creation and analysis. The project also aims to improve decision-making by providing real-time, standardized, and easily accessible data insights.

Since these two reports have been previously reviewed, we already have an understanding of their structure, data sources, and user requirements. This prior analysis significantly shortens the design phase, as key insights into layout, required metrics, and integrations have already been gathered. Instead of building dashboards from scratch, we will focus on refining existing structures, optimizing automation, and ensuring seamless data updates. This will allow for faster implementation while maintaining alignment with business needs.

Project Overview

- PowerBI Architecture Technical Set Up

  - Establish PowerBI environment/Ensure the existing environment is ready to be used.

  - Assess if PowerBI gateway is already in place or set up is needed.

- Planning Phase

  - Define business requirements.

  - Engage Deal Team to understand dashboard needs.

- Data Automation and Transformation

  - This is covered in

- Dashboard Design & Prototyping

  - Create initial mock-ups based on the files that are produced today.

  - Conduct stakeholder review with Deal Team and gather feedback.

- Development & Implementation

  - Develop interactive dashboard with automated data integration.

  - Implement filters, and user-friendly navigation.

  - Conduct user testing and refining based on feedback.

- Deployment & Training

  - Deploy dashboards to production environment.

  - Provide training sessions and user guides for business users.

  - Monitor initial usage and address any issues.

- Success Metrics

  - Reduction in manual data extraction efforts.

  - Increased user engagement with dashboards.

  - Improved decision-making based on real-time insights.

## Roles & Responsibilities

- Markman Group will be responsible for driving the business requirements gathering sessions as well as building the dashboard.

- Metropolitan will be responsible for communicating the requirements in due time as well as testing and validating dashboard output.

|  |  | RACI |  | Roles |  |
| --- | --- | --- | --- | --- | --- |
|  | Phase | Markman Group | Metropolitan | Markman Group | Metropolitan |
| 1 | PowerBI Architecture Technical Set Up | Responsible | Responsible | IT – Infrastructure Lead, PowerBI Analyst | IT |
| 2 | Planning Phase | Responsible | Accountable | PowerBI Analyst | Operations Team |
| 3 | Dashboard Design & Prototyping | Responsible | Consulted | PowerBI Analyst | Operations Team |
| 4 | Development & Implementation | Responsible | Accountable | PowerBI Analyst | Operations Team |
| 5 | Deployment & Training | Responsible | Responsible | PowerBI Analyst | Operations Team |

## Team, Effort and Pricing

| Phases | Markman Group Team | Estimated Hours | Pricing | TOTAL |
| --- | --- | --- | --- | --- |
| PowerBI Architecture Technical Setup * | Infrastructure Lead PowerBI Developer | 2,5 2,5 | $210/hr $180/hr |  |
| Planning Phase | PowerBI Developer | 10 | $180/hr |  |
| Dashboard Design and Prototyping | PowerBI Developer | 60 | $180/hr |  |
| Development & Implementation | PowerBI Developer | 60 | $180/hr |  |
| Deployment & Training | PowerBI Developer | 20 | $180/hr |  |
| Success Metrics | PowerBI Developer | 10 | $180/hr |  |
| Overall | Project Manager | 20 | $200/hr |  |
| TOTAL |  | 185 hours |  |  |

*Estimations are based on assumption that Metropolitan has PowerBI already set up and the connection with PIPE is established. If that´s not the case, we´ll need to revisit estimations based on the situation.

## Timeline

| Phases* | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 |
| --- | --- | --- | --- | --- | --- |
| PowerBI Architecture Technical Setup* |  |  |  |  |  |
| Planning Phase |  |  |  |  |  |
| Dashboard Design and Prototyping |  |  |  |  |  |
| Development & Implementation |  |  |  |  |  |
| Deployment & Training |  |  |  |  |  |
| Success Metrics |  |  |  |  |  |

*Dashboard Design and Prototyping is dependent on PowerBI Architecture Technical Set. Once the infrastructure is ready, the dashboard design can kick off.

# Visualization of PIPE via PowerBI

Project Title: Development of Business Dashboards for PIPE Data Extraction

Objective: To design and implement a dashboard visualizing PIPE information that allows business users to extract and analyze data from PIPE efficiently, improving decision-making and operational insights.

Currently, the Operations team is providing PIPE information across Metropolitan – the team needs to either manually refresh templates or create reports each time someone requests data. With the implementation of an automated dashboard, users will have real-time access to system PIPE data through a structured and standardized PowerBI interface. The dashboard will allow for on-demand data retrieval, filtering, and visualization, eliminating/minimizing the engagement on Operations side as well as the repeated manual extraction. Users can apply predefined templates and customizable views, ensuring that reports are always consistent, accurate, and aligned with business needs. This automation will reduce workload, enhance efficiency, and provide timely insights for better strategic planning.

## Project Overview

- PowerBI Architecture Technical Set Up

  - Establish PowerBI environment/Ensure the existing environment is ready to be used.

  - Ensure active connection between PIPE and PowerBI.

  - Assess if gateway is needed (PIPE data is already available on MS Fabric).

- Planning Phase

  - Define business requirements.

  - Engage stakeholders to understand dashboard needs.

  - Determine access levels and user roles.

- Dashboard Design & Prototyping

  - Create an initial mock-up leveraging the existing PIPE data model.

  - Develop a prototype with basic visualization elements.

  - Conduct stakeholder review and gather feedback.

- Development & Implementation

  - Develop interactive dashboard with real-time data integration.

  - Implement filters, and user-friendly navigation.

  - Conduct user testing and refining based on feedback.

- Deployment & Training

  - Deploy dashboards to production environment.

  - Provide training sessions and user guides for business users.

  - Monitor initial usage and address any issues.

- Success Metrics

  - Reduction in manual data extraction efforts.

  - Increased user engagement with dashboards.

  - Improved decision-making based on real-time insights.

## Scope Assumptions:

- Dashboard contains only PIPE data and does not include any modifications to the PIPE data model.

- All measures/KPIs that will be used are already incorporated into the PIPE data model.

- The dashboard will include a limited number of tabs (3-5) containing tables that will allow the end users to extract the data in excel.

- Each tab will also contain slicers, so that the end users can filter the data before extracting it.

- Security limitations (row or object level) currently are considered out of scope.

## Roles & Responsibilities

- Markman Group will be responsible for driving the business requirements gathering sessions as well as building the dashboard.

- Metropolitan will be responsible for communicating the requirements in due time as well as testing and validating dashboard output.

|  |  | RACI |  | Roles |  |
| --- | --- | --- | --- | --- | --- |
|  | Phase | Markman Group | Metropolitan | Markman Group | Metropolitan |
| 1 | PowerBI Architecture Technical Set Up | Responsible | Responsible | IT – Infrastructure Lead, PowerBI Analyst | IT |
| 2 | Planning Phase | Responsible | Accountable | PowerBI Analyst | Operations Team |
| 3 | Dashboard Design & Prototyping | Responsible | Consulted | PowerBI Analyst | Operations Team |
| 4 | Development & Implementation | Responsible | Accountable | PowerBI Analyst | Operations Team |
| 5 | Deployment & Training | Responsible | Responsible | PowerBI Analyst | Operations Team |

## Team, Effort and Pricing

| Phases | Markman Group Team | Estimated Hours | Pricing | TOTAL |
| --- | --- | --- | --- | --- |
| PowerBI Architecture Technical Setup * | Infrastructure Lead PowerBI Developer | 2,5 2,5 | $210/hr $180/hr | $525 $450 |
| Planning Phase | PowerBI Developer | 10 | $180/hr | $1,800 |
| Dashboard Design and Prototyping | PowerBI Developer | 20 | $180/hr | $3,600 |
| Development & Implementation | PowerBI Developer | 20 | $180/hr | $3,600 |
| Deployment & Training | PowerBI Developer | 10 | $180/hr | $1,800 |
| Success Metrics | PowerBI Developer | 5 | $180/hr | $900 |
| Overall | Project Manager | 8 | $200/hr | $1,600 |
| TOTAL |  | 78 hours |  | $14,275 |

*Estimations are based on assumption that Metropolitan has PowerBI already set up and the connection with PIPE is established. If that´s not the case, we´ll need to revisit estimations based on the situation.

## Timeline

| Phases* | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 |
| --- | --- | --- | --- | --- | --- |
| PowerBI Architecture Technical Setup* |  |  |  |  |  |
| Planning Phase |  |  |  |  |  |
| Dashboard Design and Prototyping |  |  |  |  |  |
| Development & Implementation |  |  |  |  |  |
| Deployment & Training |  |  |  |  |  |
| Success Metrics |  |  |  |  |  |

*Dashboard Design and Prototyping is dependent on PowerBI Architecture Technical Set. Once the infrastructure is ready, the dashboard design can kick off.

# Combined Project Approach

Should Metropolitan choose to proceed with both projects, a strategic partner discount will be applied.

| Project | Markman Group Team | Estimated Hours | PRICING TOTAL |
| --- | --- | --- | --- |
| Metropolitan DealCloud optimization project | - Business Analyst - Data Engineer - PowerBI Developer - Project Manager - Automation Developer | 252 hours | $47,280 |
| Step by Step Project Plan to utilize PIPE via PowerBI | - PowerBI Developer - Project Manager - Infrastructure Lead | 78 hours | $14,275 |
| Subtotal |  |  | $61,555 |
| Strategic Partner Discount (20%) |  |  |  |
| TOTAL |  |  | $49,244 |